## Sheet1
All Study Activity Monitoring ¦ Study Management System
Sr. No | Study No | Activity Name | Schedule Start Date | Actual Start Date | Schedule End Date | Actual End Date | Activity Status | Start Remark | End Remark | Project Manager | Sponsor Name | CR Location | BR Location | Study Type | Regulatory
1 | 23-VIN-0247 | Data BR to QA | 25 Dec 2023 | 19 Dec 2023 | 26 Dec 2023 | --- | Ongoing | - | - | Mahavir Parmar | Synthon | Vedant | Insignia | BABE | USFDA
2 | 23-VIN-0247 | BR Report BR to QA | 25 Dec 2023 | --- | 01 Jan 2024 | --- | Ongoing | - | - | Mahavir Parmar | Synthon | Vedant | Insignia | BABE | USFDA
3 | 22-VIN-0521 | Draft PB Report | 25 Dec 2023 | --- | 25 Dec 2023 | --- | Ongoing | - | - | Darshil Kanubhai Patel | PHAROS | Shivalik | Insignia | BABE | ANVISA
4 | 23-VIN-0236 | IMP Comments Resolution | 25 Dec 2023 | --- | 27 Dec 2023 | --- | Ongoing | - | - | Navalsinh Chauhan | Mint Pharma | Mehsana | Insignia | BABE | Canada
5 | 22-VIN-0479 | PB report PB to QA | 25 Dec 2023 | --- | 30 Dec 2023 | --- | Ongoing | - | - | Vipul Mangaroliya | Sandoz | Shivalik | Vedant | BABE | USFDA
6 | 23-VIN-0309 | IMP Comments Resolution | 25 Dec 2023 | 14 Aug 2023 | 27 Dec 2023 | 17 Aug 2023 | Completed | - | - | Darshil Kanubhai Patel | Lupin Limited | Mehsana | NA | BABE | EMA
7 | 23-VIN-0205 | CR Report QA to RW | 25 Dec 2023 | --- | 26 Dec 2023 | --- | Ongoing | - | - | Deval Soni | Almatica Pharma LLC | Mehsana | Insignia | BABE | USFDA
8 | 23-VIN-0205 | BR Report BR to QA | 25 Dec 2023 | --- | 29 Dec 2023 | --- | Ongoing | - | - | Deval Soni | Almatica Pharma LLC | Mehsana | Insignia | BABE | USFDA
9 | 23-VIN-0205 | Data PB to QA | 25 Dec 2023 | --- | 25 Dec 2023 | --- | Ongoing | - | - | Deval Soni | Almatica Pharma LLC | Mehsana | Insignia | BABE | USFDA
10 | 22-VIN-0455 | Data BR to QA | 25 Dec 2023 | --- | 25 Dec 2023 | --- | Ongoing | - | - | Vipul Mangaroliya | Sandoz | Vedant | Vedant | BABE | USFDA
11 | 22-VIN-0455 | Data QA to BR | 25 Dec 2023 | --- | 25 Dec 2023 | --- | Ongoing | - | - | Vipul Mangaroliya | Sandoz | Vedant | Vedant | BABE | USFDA
12 | 22-VIN-0455 | Data BR to PB | 25 Dec 2023 | --- | 25 Dec 2023 | --- | Ongoing | - | - | Vipul Mangaroliya | Sandoz | Vedant | Vedant | BABE | USFDA
13 | 22-VIN-0455 | BR Report BR to QA | 25 Dec 2023 | --- | 01 Jan 2024 | --- | Ongoing | - | - | Vipul Mangaroliya | Sandoz | Vedant | Vedant | BABE | USFDA
14 | 23-VIN-0314 | PB report PB to QA | 25 Dec 2023 | --- | 30 Dec 2023 | --- | Ongoing | - | - | Praful Talaviya | ELPEN | Vedant | Insignia | BABE | EU
15 | 23-VIN-0114 | Tentative Clinic Date | 25 Dec 2023 | --- | 25 Dec 2023 | --- | Ongoing | - | - | Archana Gosai | DRL | Shivalik | Insignia | BABE | ANVISA
16 | 23-VIN-0312 | Data CR to RW | 25 Dec 2023 | --- | 01 Jan 2024 | --- | Ongoing | - | - | Praful Talaviya | ELPEN | Vedant | Insignia | BABE | EU
17 | 22-VIN-0427 | Draft PB Report | 25 Dec 2023 | --- | 25 Dec 2023 | --- | Ongoing | - | - | Praful Talaviya | Gador | Vedant | Vedant | BABE | EU
18 | 23-VIN-0281 | Bioanalytical Analysis | 25 Dec 2023 | --- | 06 Jan 2024 | --- | Ongoing | - | - | Vipul Mangaroliya | Sandoz | Vedant | Insignia | BABE | USFDA
19 | 23-VIN-0387 | IEC Submission | 25 Dec 2023 | --- | 28 Dec 2023 | --- | Ongoing | - | - | Yajuvendrasinh Solanki | Torrent | Vedant | Vedant | Comaparative Bio Availabity | USFDA
20 | 23-VIN-0383 | Data BR to PB | 25 Dec 2023 | 23 Dec 2023 | 25 Dec 2023 | 23 Dec 2023 | Completed | - | - | Mahavir Parmar | Jamp Pharma | Shivalik | Insignia | BABE | Canada
21 | 23-VIN-0170 | Checkin (P2) | 25 Dec 2023 | --- | 25 Dec 2023 | --- | Ongoing | - | - | Praful Talaviya | Avion | Vedant | Insignia | Comaparative Bio Availabity | USFDA
22 | 23-VIN-0328 | IEC Approval | 25 Dec 2023 | --- | 10 Jan 2024 | --- | Ongoing | - | - | Praful Talaviya | Orbicular | Vedant | NA | Comaparative Bio Availabity | USFDA
23 | 23-VIN-0410 | Checkin (P2) | 25 Dec 2023 | 25 Dec 2023 | 25 Dec 2023 | --- | Ongoing | - | - | Darshil Kanubhai Patel | Lupin Limited | Vedant | NA | BABE | USFDA
24 | 23-VIN-0410 | IEC Submission Confirmation from PM | 25 Dec 2023 | 18 Sep 2023 | 25 Dec 2023 | 18 Sep 2023 | Completed | - | - | Darshil Kanubhai Patel | Lupin Limited | Vedant | NA | BABE | USFDA
25 | 23-VIN-0411 | IEC Submission Confirmation from PM | 25 Dec 2023 | 18 Oct 2023 | 25 Dec 2023 | 18 Oct 2023 | Completed | - | - | Darshil Kanubhai Patel | Lupin Limited | Mehsana | NA | BABE | USFDA
26 | 23-VIN-0412 | IEC Submission Confirmation from PM | 25 Dec 2023 | 18 Oct 2023 | 25 Dec 2023 | 18 Oct 2023 | Completed | - | - | Darshil Kanubhai Patel | Lupin Limited | Mehsana | NA | BABE | USFDA
27 | 23-VIN-0408 | CR Report QA to RW | 25 Dec 2023 | 25 Dec 2023 | 27 Dec 2023 | --- | Ongoing | - | - | Jigar Parikh | Sunpharma | Shivalik | Sponsor Facility | BABE | NPRA
28 | 23-VIN-0503 | IMP Availibility | 25 Dec 2023 | --- | 03 Jan 2024 | --- | Ongoing | - | - | Navalsinh Chauhan | LAROPHARM, Romania | Shivalik | Vedant | BABE | EMA
29 | 23-VIN-0507 | IEC Approval | 25 Dec 2023 | 01 Dec 2023 | 08 Jan 2024 | 05 Dec 2023 | Completed | - | - | Mahavir Parmar | Crescent Pharma Ltd | Vedant | Vedant | BABE | EMA
30 | 23-VIN-0509 | IEC Submission | 25 Dec 2023 | --- | 28 Dec 2023 | --- | Ongoing | - | - | Mahavir Parmar | Jamp Pharma | Vedant | Vedant | BABE | Canada
31 | 22-VIN-0427_UN | Data BR to QA | 25 Dec 2023 | --- | 26 Dec 2023 | --- | Ongoing | - | - | Praful Talaviya | Gador | Vedant | Vedant | BABE | EU
32 | 23-VIN-0492 | DCGI Submission NOC + TL | 25 Dec 2023 | 10 Nov 2023 | 26 Dec 2023 | 10 Nov 2023 | Completed | - | - | Darshil Kanubhai Patel | Lupin Limited | Mehsana | Sponsor Facility | BABE | Canada
33 | 23-VIN-0493 | DCGI Submission NOC + TL | 25 Dec 2023 | 10 Nov 2023 | 26 Dec 2023 | 10 Nov 2023 | Completed | - | - | Darshil Kanubhai Patel | Lupin Limited | Mehsana | Sponsor Facility | BABE | Canada
34 | 23-VIN-0477 | IEC Approval | 25 Dec 2023 | 29 Nov 2023 | 08 Jan 2024 | 07 Dec 2023 | Completed | - | - | Vipul Mangaroliya | Sandoz | Vedant | Vedant | BABE | USFDA
35 | 23-VIN-0409 | CR Report QA to RW | 25 Dec 2023 | --- | 27 Dec 2023 | --- | Ongoing | - | - | Jigar Parikh | Sunpharma | Shivalik | Sponsor Facility | BABE | NPRA
36 | 23-VIN-0101 | PB report PB to QA | 25 Dec 2023 | --- | 30 Dec 2023 | --- | Ongoing | - | - | Manish Chaurasia | Pharmathen | Mehsana | Vedant | BABE | EU
37 | 23-VIN-0102 | PB report PB to QA | 25 Dec 2023 | --- | 30 Dec 2023 | --- | Ongoing | - | - | Manish Chaurasia | Pharmathen | Mehsana | Vedant | BABE | EU
38 | 23-VIN-0248-G1 | Data CR to QA | 25 Dec 2023 | --- | 04 Jan 2024 | --- | Ongoing | - | - | Yajuvendrasinh Solanki | Torrent | Shivalik | Sponsor Facility | BABE | EU
39 | 23-VIN-0280 | Checkin | 25 Dec 2023 | --- | 25 Dec 2023 | --- | Ongoing | - | - | Archana Gosai | Pharmathen S.A | Mehsana | Insignia | BABE | EMA
40 | 23-VIN-0534 | DCGI Submission NOC + TL | 25 Dec 2023 | --- | 26 Dec 2023 | --- | Ongoing | - | - | Navalsinh Chauhan | Helba | Mehsana | Vedant | BABE | EU
41 | 23-VIN-0398 | Data CR to RW | 25 Dec 2023 | --- | 26 Dec 2023 | --- | Ongoing | - | - | Praful Talaviya | Inventia | Shivalik | Insignia | BABE | EU
42 | 23-VIN-0306 | IMP Comments Resolution | 25 Dec 2023 | --- | 27 Dec 2023 | --- | Ongoing | - | - | Vipul Mangaroliya | MSN | Shivalik | Insignia | BABE | TGA
43 | 23-VIN-0307 | IMP Comments Resolution | 25 Dec 2023 | --- | 27 Dec 2023 | --- | Ongoing | - | - | Vipul Mangaroliya | MSN | Shivalik | Insignia | BABE | TGA
44 | 23-VIN-0565 | IEC Submission | 25 Dec 2023 | --- | 28 Dec 2023 | --- | Ongoing | - | - | Deval Soni | Deva | Vedant | Vedant | BABE | EU
45 | 23-VIN-0370 | Data CR to RW | 25 Dec 2023 | --- | 01 Jan 2024 | --- | Ongoing | - | - | Jigar Parikh | Sunpharma | Shivalik | NA | BABE | ANVISA
46 | 23-VIN-0012-G1 | Data CR to QA | 25 Dec 2023 | --- | 28 Dec 2023 | --- | Ongoing | - | - | Jigar Parikh | Genetic SpA | Vedant | Vedant | BABE | EU
47 | 23-VIN-0346 | Protocol Finalization | 25 Dec 2023 | 12 Dec 2023 | 28 Dec 2023 | 14 Dec 2023 | Completed | - | - | Navalsinh Chauhan | Eugia Pharma / APL | Vedant | Vedant | BABE | USFDA
48 | 23-VIN-0371 | IMP Availibility | 25 Dec 2023 | 15 Dec 2023 | 25 Dec 2023 | 20 Dec 2023 | Completed | - | - | Jigar Parikh | Sunpharma | Shivalik | NA | BABE | ANVISA
49 | 23-VIN-0592 | MD/MV | 25 Dec 2023 | --- | 30 Jan 2024 | --- | Ongoing | - | - | Archana Gosai | DRL | Shivalik | Vedant | BABE | NMPA
50 | 23-VIN-0593 | MD/MV | 25 Dec 2023 | --- | 30 Jan 2024 | --- | Ongoing | - | - | Archana Gosai | DRL | Shivalik | Vedant | BABE | NMPA
51 | 23-VIN-0315-G2 | Checkin (P2) | 25 Dec 2023 | --- | 25 Dec 2023 | --- | Ongoing | - | - | Praful Talaviya | ELPEN | Shivalik | Insignia | BABE | EU
52 | 23-VIN-0012-G3 | Dosing (P2) | 25 Dec 2023 | 25 Dec 2023 | 25 Dec 2023 | 25 Dec 2023 | Completed | - | - | Jigar Parikh | Genetic SpA | Vedant | Vedant | BABE | EU
53 | 22-VIN-0427_NOM | Data BR to PB | 25 Dec 2023 | 20 Dec 2023 | 25 Dec 2023 | 20 Dec 2023 | Completed | - | - | Praful Talaviya | Gador | Vedant | Vedant | BABE | EU