## Sheet1
All Study Activity Monitoring ¦ Study Management System
Sr. No | Study No | Activity Name | Schedule Start Date | Actual Start Date | Schedule End Date | Actual End Date | Activity Status | Start Remark | End Remark | Project Manager | Sponsor Name | CR Location | BR Location | Study Type | Regulatory
1 | 22-VIN-0021-G1 | Data QA to CR | 24 Nov 2022 | 24 Nov 2022 | 30 Nov 2022 | 12 Dec 2022 | Completed | - | Other - Delay CR | Mahavir Parmar | Lamda | Vedant | Insignia | BABE | EU
2 | 22-VIN-0021 | Data QA to CR | 30 Nov 2022 | 30 Nov 2022 | 07 Dec 2022 | 16 Dec 2022 | Completed | - | Other - delay | Mahavir Parmar | Lamda | Vedant | Insignia | BABE | EU
5 | 22-VIN-0021 | CR Report QA to RW | 21 Dec 2022 | 21 Dec 2022 | 25 Dec 2022 | 29 Jan 2023 | Completed | - | Other - Delay | Mahavir Parmar | Lamda | Vedant | Insignia | BABE | EU
9 | 22-VIN-0021 | Data QA to PB | 11 Jan 2023 | 11 Jan 2023 | 11 Jan 2023 | 11 Jan 2023 | Completed | - | - | Mahavir Parmar | Lamda | Vedant | Insignia | BABE | EU
13 | 22-VIN-0021 | PB report QA to PB | 23 Jan 2023 | 23 Jan 2023 | 25 Jan 2023 | 25 Jan 2023 | Completed | - | - | Mahavir Parmar | Lamda | Vedant | Insignia | BABE | EU